## Dashboard
KWSP i-Akaun UX Audit - Project Dashboard
Live tracker: overall progress, health, mandays and key alerts · Auto-updates from all sheets
Project Start Date: | 2026-05-06 | <- Enter project start date here | End Date: | 2026-09-11 | ← auto: Start + 14 weeks | Today: | 2026-06-08 |  | UXR Lead: | Faznur | Status: | Delayed
OVERALL PROGRESS |  |  | TASKS COMPLETE |  |  | TASKS DELAYED |  |  | MANDAYS USED |  | MANDAYS REMAINING
11.38% |  |  | 3 |  |  | 1 |  |  | 27.7789 |  | 216.2211
Workstream | Weeks | Total Tasks | Complete | In Progress | Not Started | % Done | Status | Expected Start | Expected End
Setup | W0-W4 | 5 | 2 | 0 | 2 | 77.91% | Delayed | 2026-05-06 | 2026-06-22
Heuristics Study | W4-W7 | 6 | 0 | 0 | 6 | 0% | Not Started | 2026-06-18 | 2026-07-13
Analytics Review | W4-W6 | 3 | 0 | 0 | 3 | 0% | Not Started | 2026-06-18 | 2026-07-06
Benchmarking and Peer Study | W4-W6 | 2 | 0 | 0 | 2 | 0% | Not Started | 2026-06-18 | 2026-07-06
Field Research | W6-W11 | 7 | 0 | 0 | 7 | 0% | Not Started | 2026-07-07 | 2026-08-11
Analysis | W11-W13 | 5 | 0 | 0 | 5 | 0% | Not Started | 2026-08-12 | 2026-08-27
Recommendations | W13-W15 | 6 | 0 | 0 | 6 | 0% | Not Started | 2026-08-28 | 2026-09-09
Reporting | W15 | 2 | 0 | 0 | 2 | 0% | Not Started | 2026-09-10 | 2026-09-11
TOTAL |  | 36 | 2 | 0 | 33 | 5.556%
S
Role | Total Mandays Planned | Mandays Used | Remaining | % Used
UXR Lead | 57 | 17.92 | 39.08 | 31.44%
UXR Ast | 61 | 3 | 0 | 4.918%
Data Team | 10 | 0 | 0 | 0%
All (Total) | 128 | 20.92 | 107.08 | 16.34%
Formulas:
Expected Start = IFERROR(MIN(_xlws.FILTER('Task Tracker'!$I8:I203,TRIM('Task Tracker'!$B8:B203)=TRIM([OVERALL PROGRESS]))),"")
MANDAYS USED = IFERROR(MAX(_xlws.FILTER('Task Tracker'!$J8:J203,TRIM('Task Tracker'!$B8:B203)=TRIM([OVERALL PROGRESS]))),"")

## Task Tracker
KWSP i-Akaun UX Audit - Task Tracker
# | Workstream | Owner | Task / Deliverable | Plan Start (Week) | Plan End (Week) | Task concurrency | Mandays | Plan Start | Plan End | Start Date | Actual End | Status | % Complete | Days Delayed | Off days taken | Notes / Blockers | URL Files
1 | Setup | UXR Lead | Research Planning | W0 | W1 |  | 8 | 2026-05-06 | 2026-05-18 | 2026-05-04 | 2026-05-19 | Delayed | 99% | 1 | 5 | Pending Microservices list to shortlist - from data team
2 | Setup | UXR Lead | HOS & HOD Approval on Research Plan | W1 | W2 |  | 7 | 2026-05-19 | 2026-06-03 | 2026-05-22 | 2026-05-26 | Completed Early | 100% | 0 | 9
3 | Setup | UXR Lead, UXR Ast | Resource Hunting + Material Prep | W3 | W3 |  | 3 | 2026-06-04 | 2026-06-08 | 2026-05-27 | 2026-06-05 | Completed Early | 100% | 0 | 2 | Faz send email to all HOU > Suvi follow-up
4 | Checkpoint | UXR Lead, UXR Ast | Debriefing to working team + assimilation | W3 | W4 |  | 3 | 2026-06-09 | 2026-06-17 |  |  | Starts in 1 day | 0% | - | 6
5 | Setup | UXR Lead | Request RCM + IM Data | W4 | W4 |  | 3 | 2026-06-18 | 2026-06-22 |  |  | Not Started | 0% | - | 2 | Pn Zanita / Pn Jamilah
6 | Setup | UXR Lead | RCM + Data Analysis | W4 | W4 | 4 | 2 | 2026-06-18 | 2026-06-19 |  |  | Not Started | 0% | - | 0 | Faizul Azhair
7 | Heuristics Study | UXR Ast | Conduct Nielsen's 10 Usability Heuristics | W4 | W5 | 4 | 5 | 2026-06-18 | 2026-06-29 |  |  | Not Started | 0% | - | 7
8 | Heuristics Study | UXR Ast | Conduct Mobile-specific usability principles | W5 | W5 |  | 2 | 2026-06-30 | 2026-07-01 |  |  | Not Started | 0% | - | 0 | Touch targets, gestures, orientation, loading states, offline behaviour
9 | Heuristics Study | UXR Ast | Conduct app trust & security standards | W5 | W5 |  | 1 | 2026-07-02 | 2026-07-02 |  |  | Not Started | 0% | - | 0 | Custom checklist — error messaging, confirmations, transparency
10 | Heuristics Study | UXR Ast | Conduct WCAG 2.1 AA accessibility compliance | W5 | W5 |  | 1 | 2026-07-03 | 2026-07-03 |  |  | Not Started | 0% | - | 0 | Automated tools (axe, WAVE) + manual walkthrough with screen readers. Benchmark with other apps. Population affected. Special case for security: password for blind people how secure if read out
11 | Heuristics Study | UXR Ast/Content | Conduct Content & language clarity | W6 | W6 |  | 2 | 2026-07-06 | 2026-07-07 |  |  | Not Started | 0% | - | 0 | Tone, reading level, multi-language quality across all screens
12 | Heuristics Study | UXR Ast/UIUX | Conduct Design consistency audit | W6 | W7 |  | 4 | 2026-07-08 | 2026-07-13 |  |  | Not Started | 0% | - | 2 | UI patterns, spacing, typography, iconography
13 | Analytics Review | Data Team | Conduct In-app analytics | W4 | W4 | 4 | 4 | 2026-06-18 | 2026-06-23 |  |  | Not Started | 0% | - | 2 | User profile, overview
14 | Analytics Review | Data Team | Conduct Drop-off / funnel analysis | W5 | W5 |  | 4 | 2026-06-29 | 2026-07-02 |  |  | Not Started | 0% | - | 0
15 | Analytics Review | Data Team | Conduct App crash and error reports | W5 | W6 |  | 2 | 2026-07-03 | 2026-07-06 |  |  | Not Started | 0% | - | 2
16 | Benchmarking and Peer Study | UXR Lead | Conduct Competitive Benchmarking | W4 | W5 | 4 | 7 | 2026-06-18 | 2026-07-01 |  |  | Not Started | 0% | - | 7 | Feature comparison matrix, Visual and UI design quality, accessibility benchmarking, Information architecture, App store UX review mining, Innovation gap analysis
17 | Benchmarking and Peer Study | UXR Lead | Build feature comparison matrix | W5 | W6 |  | 3 | 2026-07-02 | 2026-07-06 |  |  | Not Started | 0% | - | 2
18 | Field Research | UXR Ast | Finalise UT Plan & Endorsement | W6 | W6 | 17 | 3 | 2026-07-07 | 2026-07-09 |  |  | Not Started | 0% | - | 0
19 | Field Research | UXR Ast | Prototype and Question Readiness | W6 | W8 |  | 8 | 2026-07-10 | 2026-07-21 |  |  | Not Started | 0% | - | 4 | Prototype: 8 days, Questions: 5 days
20 | Field Research | UXR Ast | Moderator Recruitment | W8 | W8 |  | 3 | 2026-07-22 | 2026-07-24 |  |  | Not Started | 0% | - | 0
21 | Field Research | UXR Ast | Branch Engagement + Confirmation | W6 | W6 | 17 | 3 | 2026-07-07 | 2026-07-09 |  |  | Not Started | 0% | - | 0
22 | Field Research | UXR Ast | UT Materials Prep + Dry Run | W6 | W7 |  | 3 | 2026-07-10 | 2026-07-14 |  |  | Not Started | 0% | - | 2
23 | Field Research | UXR Ast | UT Field day | W7 | W10 |  | 15 | 2026-07-15 | 2026-08-04 |  |  | Not Started | 0% | - | 6 | Malaysia Assoc Blind
24 | Field Research | UXR Ast | UT Report Compilation | W10 | W11 |  | 5 | 2026-08-05 | 2026-08-11 |  |  | Not Started | 0% | - | 2
25 | Analysis | UXR Lead | Consolidate Findings | W11 | W12 |  | 5 | 2026-08-12 | 2026-08-18 |  |  | Not Started | 0% | - | 2
26 | Analysis | UXR Lead | Build consolidated issue list (remove duplicates) | W12 | W12 |  | 1 | 2026-08-19 | 2026-08-19 |  |  | Not Started | 0% | - | 0
27 | Analysis | UXR Lead | Score issues: severity × frequency × impact | W12 | W12 |  | 1 | 2026-08-20 | 2026-08-20 |  |  | Not Started | 0% | - | 0
28 | Analysis | UXR Lead | Draft 4–5 user personas from research data | W12 | W13 |  | 2 | 2026-08-21 | 2026-08-25 |  |  | Not Started | 0% | - | 3
29 | Analysis | UXR Lead | Draw current-state journey maps (top 5 flows) | W13 | W13 |  | 2 | 2026-08-26 | 2026-08-27 |  |  | Not Started | 0% | - | 0
30 | Recommendations | UXR Lead | Build effort vs. impact matrix for all recommendations | W13 | W13 |  | 2 | 2026-08-28 | 2026-09-01 |  |  | Not Started | 0% | - | 3
31 | Recommendations | UXR Lead | Identify 10–15 quick wins | W14 | W14 |  | 1 | 2026-09-02 | 2026-09-02 |  |  | Not Started | 0% | - | 0
32 | Recommendations | UXR Lead | Identify 3–5 strategic initiatives | W14 | W14 |  | 1 | 2026-09-03 | 2026-09-03 |  |  | Not Started | 0% | - | 0
33 | Recommendations | UXR Lead | Build phased 12-month implementation roadmap | W14 | W14 |  | 1 | 2026-09-04 | 2026-09-04 |  |  | Not Started | 0% | - | 0
34 | Recommendations | UXR Lead | Slide touch up and summary | W14 | W14 |  | 2 | 2026-09-07 | 2026-09-08 |  |  | Not Started | 0% | - | 0
35 | Recommendations | UXR Lead | Internal Sharing | W15 | W15 |  | 1 | 2026-09-09 | 2026-09-09 |  |  | Not Started | 0% | - | 0
36 | Reporting | UXR Lead | Incorporate review feedback into final report | W15 | W15 |  | 1 | 2026-09-10 | 2026-09-10 |  |  | Not Started | 0% | - | 0
37 | Reporting | UXR Lead | Presentation Week | W15 | W15 |  | 1 | 2026-09-11 | 2026-09-11 |  |  | Not Started | 0% | - | 0
TOTAL MANDAYS | [6 empty] | 122 | [5 empty] | 8.081%
Formulas:
Plan Start (Week) = IF(ISNUMBER([Plan Start]),"W"&MAX(0,INT((NETWORKDAYS(Dashboard!$B3,[Plan Start],offday[Date])-1)/5)),"")
Plan End (Week) = IF(ISNUMBER([Plan End]),"W"&MAX(0,INT((NETWORKDAYS(Dashboard!$B3,[Plan End],offday[Date])-1)/5)),"")
Plan Start = IF([Mandays]="","",IF(ROW()=8,Dashboard!$B3,IF([Task concurrency]="",IFERROR(WORKDAY([Plan End, row above],1,offday[Date]),"Check Predecessor"),IFERROR(WORKDAY(INDEX(J8:J203,MATCH([Task concurrency],A8:A203,0)),1,offday[Date]),"Check Predecessor"))))
Plan End = IF([Mandays]="","",IF(ISNUMBER([Plan Start]),WORKDAY([Plan Start],[Mandays]-1,offday[Date]),"Check Predecessor"))
Days Delayed = IFERROR(IF(NOT(ISNUMBER([Plan End])),"",IF(AND([Actual End]<>"",ISNUMBER([Actual End]),[Actual End]<=TODAY()),MAX(0,NETWORKDAYS([Plan End],[Actual End],offday[Date])-1),IF(TODAY()>[Plan End],MAX(0,NETWORKDAYS([Plan End],TODAY(),offday[Date])-1),"-"))),"-")
Off days taken = IF(OR(NOT(ISNUMBER([Plan Start])),NOT(ISNUMBER([Plan End]))),"",([Plan End]-[Plan Start]+1)-NETWORKDAYS([Plan Start],[Plan End],offday[Date]))
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Suvinithira a/p Nadesan shouldn’t take more than 2 days for app trust and security standards & WCAG. 1 day is enough. Its not that difficult.
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Suvinithira a/p Nadesan , all this (18-20) can run concurrently, putting in mind that you have proteges to assist you with the arrangements

## MY Holidays
Malaysia Federal Public Holidays - 2025 & 2026
Named range 'MYHolidays' = A4:A60 · Formula: =WORKDAY(M11, D11, MYHolidays) · Add state holidays in yellow rows below
Date | Holiday Name | Type | Day
01/01/2026 | New Year's Day | 2026 | Thu
2026-01-29 | Chinese New Year | 2026 | Thu
2026-01-30 | Chinese New Year (2nd day) | 2026 | Fri
2026-03-20 | Hari Raya Aidilfitri | 2026 | Fri
2026-03-21 | Hari Raya Aidilfitri (2nd day) | 2026 | Sat
2026-03-23 | Hari Raya Aidilfitri (in lieu) | 2026 | Mon
2026-05-01 | Labour Day | 2026 | Fri
2026-05-27 | Hari Raya Aidiladha | 2026 | Thu
2026-05-31 | Wesak Day | 2026 | Sun
2026-06-01 | Yang di-Pertuan Agong's Birthday | 2026 | Mon
2026-06-15 | Awal Muharram (Islamic New Year) | 2026 | Mon
2026-08-24 | Prophet Muhammad's Birthday | 2026 | Mon
2026-08-31 | National Day (Merdeka) | 2026 | Mon
2026-09-16 | Malaysia Day | 2026 | Wed
2026-11-08 | Deepavali | 2026 | Sun
2026-11-09 | Deepavali (in lieu) | 2026 | Mon
2026-12-25 | Christmas Day | 2026 | Fri
2026-05-08 | Suvi OOO | 2026 | Fri
2026-06-02 | Carry forward Wesak | 2026 | Tue
2026-06-24 | Suvi OOO | 2026 | Wed
2026-06-25 | Suvi OOO | 2026 | Thu
2026-06-26 | Suvi OOO | 2026 | Fri
2026-09-17 | Suvi OOO | 2026 | Thu
2026-09-18 | Suvi OOO | 2026 | Fri
2026-05-28 | Faz OOO | 2026 | Thu
2026-05-29 | Faz OOO | 2026 | Fri
2026-06-10 | UT i-Invest | 2026 | Wed
2026-06-11 | UT i-Invest | 2026 | Thu
2026-06-12 | UT i-Invest | 2026 | Fri
READY-TO-USE FORMULAS
Actual End Date from Start + Mandays (excl. weekends & PH) |  | WORKDAY( ActualStart , Mandays , MYHolidays )
Working days between two dates (excl. weekends & PH) |  | NETWORKDAYS( StartDate , EndDate , MYHolidays ) - 1
Days overrun - actual vs planned end (working days) |  | MAX( 0 , NETWORKDAYS( PlannedEnd , ActualEnd , MYHolidays ) - 1 )
Planned end date from project start + week number |  | WORKDAY( ProjectStart , WeekNum * 5 , MYHolidays )